# HOUSING CAPITAL PROGRAMME 2011/2012

# Information for the Tenants Forum

## The housing capital programme helps the Council to keep its property in good condition and to develop new affordable homes. It also plays an important role in improving the quality of life for tenants.

## This report provides information for the Tenants Forum about the major projects that we are planning to undertake during 2011/2012.

All social housing is required by the Government to meet the ‘Decent Homes’ standard. To meet the standard, a property must:

- meet the statutory fitness standard;

- be in good repair;

- have a modern bathroom and kitchen;

- be reasonably easy to keep warm;

All the Council’s housing stock now meets the target.  This compares well with the rest of the country where 92% of council housing meets the Decent Home standard.

During 2011/2012, we are planning to invest over £2.460 million in improving your homes. This will enable us to improve over 646 homes, which equates to 17% of our housing stock. We will:

- refurbish kitchens and bathrooms in 65 homes;

- install new windows in 64 homes;

- replace 25 central heating systems;

- install new external doors to 92 homes.

The Council’s Executive Committee will be asked to approve our capital programme for 2011/12 at its next meeting, which takes place on February 16.

In addition to our plans for capital investment, we are planning to spend a total of £3.296 million in 2011/12 on day-to-day repairs. This compares to expenditure of £3.343 million on repairs in this financial year. The reduction   is the result of the Housing Revenue Account subsidy settlement which has resulted in an increase of £900,000 in the amount that the Council will have to pay to the Government in 2012.

A total of £50,000 will be available for Neighbourhood Managers to spend on estate improvements during 2010/12.

Regular updates on our progress in implementing the capital programme will be provided for the Tenants Forum Monitoring group and the Tenants Forum throughout the year.

John Conway

Head of Housing

| Project No. | Project Name | No of Homes | Works Cost £000’s | Start | Completion | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| H443 | Replacement of pitched roof coverings This is part of a five year programme to replace tiled roofs and upgrade insulation to properties which were built between 1945 and 1960 | 60 | 145 | May11 | Sept 11 | Centre Parade, Kettering Top Dysons, Cranford Hilltop Close, Desborough Meadow Road, Rothwell |
| H441 | Installation of PVC-U frame windows Final phase of a programme to replace double glazed timber frame windows to properties which were built during the 1980’s and early 1990’s | 64 | 135 | Jun | Sept 11 | Jasmine Court The Lawns |
| H446 | Installation of composite GRP door sets Continuation of a programme to replace timber doors in order to provide better security and thermal efficiency. | 92 | 205 | April 11 | Nov 11 | Rothwell Grange Estate |
| H435 | Refurbishment of kitchens and bathrooms Latest phase of a rolling programme to replace outworn kitchens and bathrooms | 59 | 398 | May 11 | Dec 11 | Rothwell West Phase 2 – Edinburgh Close and Elizabeth Road Ad hoc installations |
| H449 | Villages – External wall insulation Two year programme to install external wall insulation to village properties without cavity walls in order to improve thermal insulation | 11 | 99 | Jun 11 | Aug 11 | Ashley, Braybrook, Cranford, Cransley, Loddington |
| H458 | Loft and cavity wall insulation Catch-up programme of insulation for properties across the borough which were not included in previous contracts | - | 125 | Apr 11 | Mar 12 | Various locations throughout the Borough |
| H442 | Central heating renewal Replacement of older central heating systems with more efficient and modern equipment | - | 100 | Apr 11 | Mar 12 | Various locations throughout the Borough |
| H430 | Testing and renewal of electrical circuits Upgrading electrical installations so that they meet modern standards | 725 | 91 | Apr 11 | Mar 12 | Various locations throughout the Borough |
| H456 | Replacement of fire doors Replacement of entrance doors to flats in 3 storey blocks | 200 | 152 | Nov 11 | Mar 12 | Various locations throughout the Borough |
| H | Judith Road maisonettes – fire precautions Improving the means of escape from 3 storey maisonettes | 12 | 53 | July 11 | Sept 11 | Judith Road maisonettes |
| H | External wall repairs Year 1 of an eight year rolling programme to repair external walls and chimney stacks | 76 | 23 | May 11 | Mar 12 | Highfield Road – Pre 1945 properties |
| H457 | Decent homes works Works to properties which potentially will fail the decent homes standard in 2011/2012 | 12 | 33 | Apr 11 | Mar 12 | Various locations throughout the Borough |
| H448 | Structural repairs and installation of damp proof courses Ad hoc structural works to properties across the borough | - | 136 | Apr 11 | Mar 12 | Various locations throughout the Borough |
| H440 | Door entry systems Improving home security by installing new door entry systems | - | 31 | Apr 11 | Mar 12 | Various locations throughout the Borough |
| H420 | Improving access for disabled people Adapting council homes to make life easier for disabled people | - | 272 | Apr 11 | Mar 12 | Various locations throughout the Borough |
| H451 | Rosewood Place – environmental improvements Installation of front door canopies, construction of off-road parking spaces and new boundary walls and fences. | 18 | 154 | Feb 11 | Aug 11 | Rosewood Place |
| H450 | Highfield Road – Environmental Improvements Making Highfield Road a safer and more attractive place to live by improving security and constructing new boundary walls and bin stores | - | 30 | April 11 | May 11 | 115 – 129 Highfield Road |
| H455 | Replacement of oil tanks Replacement of tanks serving oil-fired central heating systems in vlllage locations | - | 36 | Apr 11 | Mar 12 | Various locations throughout the Borough |

# Text boxes

## Decent Homes Programme

## Investment Plans for 2011/2012

## Revenue Spending in 20011/2012

## Monitoring the Success of the Programme

HOUSING CAPITAL PROGRAMME 2011/2012 – HRA PROJECTS